## Set the Stage
Check In - How do you think the project/iteration went? (use one word)
Challenging
Stimulating
Well organized

## Gather Data
Start/Stop/Continue
START |  | CONTINUE |  | STOP
A new idea, something that you have seen worked well and that you would like to present. Something that was mentioned during the work but that was not undertaken in a structured way. |  | Something that has been done and in which the team recognizes value. What are the positive things that have been undertaken in the job or what are the things the team would miss if they weren't there? |  | All those things that do not bring value or that compromise productivity. What are those things that would be better to get rid of?
Participation in analysis meetings | 1 | Well-described stories | 4 | Deviation from the designed graphics | 2
|  | Pair programming | 3 | Huge Pull Requests | 3

## Generate Insight & Decide What
Actions | In charge | Deadline
Feedback on tasks not fully described | Stefano | 23/3/20
Increase the Pair Programming hours | Riccardo | 25/3/20
Improve dialoge with UX/UI team | Giulia | 2020-02-04
NOTES

## Close the Retrospective
Return of Time Invested
ROTI
1 - I wasted time | 0
2 - It was slightly useful | 0
3 - It was useful but nothing special | 2
4 - It was useful | 3
5 - It was very useful | 1